## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Sheet 1
| Table 3 | Sheet 1 - Table 3
| Table 5 | Sheet 1 - Table 5
| Table 1 | Sheet 1 - Table 1
| Table 4 | Sheet 1 - Table 4
| Table 5-1 | Sheet 1 - Table 5-1
| Table 5-1-1 | Sheet 1 - Table 5-1-1
| Table 5-1-2 | Sheet 1 - Table 5-1-2
| Table 2 | Sheet 1 - Table 2

## Sheet 1 - Table 3
| Table data download | [5 empty] | Total
| Plan and test download function | Implement table serialisation | Develop web services | Proxy development | User interface | User feedback and testing
Milko | 1 | 2 | 2 |  |  | 1 | 6
Alessandro | 1 |  |  | 3 | 2 | 1 | 7
Total days | 7

## Sheet 1 - Table 5
| Login system | [9 empty] | Total
| Planning and analysis | Develop web services | Develop user permissions routines | User create, modify and delete interfaces | Develop the user storage system | User transaction management interface | User permissions interface | User storage management interface | User data validation management interface | User feedback and testing
Milko | 1 | 3 | 2 |  | 8 |  |  |  |  | 2 | 16
Alessandro | 1 |  |  | 5 |  | 3 | 2 | 2 | 3 | 2 | 18
Total days | 18

## Sheet 1 - Table 1
|  | Dataset upload system | [11 empty] | Total
| Planning and analysis | Develop dataset storage | Develop storage web services | Develop Security procedures | Develop validation | Dataset management and version control interface | Develop data modification routines and web services | Data validation feedback interface | Data create, modify and delete interface | Develop routines and services to transfer data to public portal | Data publication interface | Integrate download system in data warehouse | User feedback and testing
Milko | 2 | 4 | 2 |  | 7 |  | 5 |  |  | 4 |  | 2 | 4 | 30
Alessandro | 2 |  |  | 2 |  | 5 |  | 3 | 5 |  | 2 | 1 | 4 | 24
Total days |  | 30

## Sheet 1 - Table 4
| Template data download | [5 empty] | Total
| Planning and analysis | Develop object formatting routines | Develop web services | Proxy development | User interface | User feedback and testing
Milko | 1 | 8 | 1 |  |  | 2 | 12
Alessandro | 1 |  |  | 2 | 1 | 2 | 6
Total days | 12

## Sheet 1 - Table 5-1
| Portal management |  |  |  |  | Total
| Planning and analysis | Develop content editor | Develop upload system for attachments | Develop static content full text search | User feedback and testing
Milko | 1 |  |  | 2 | 1 | 4
Alessandro | 1 | 2 | 2 | 1 | 2 | 8
Total days | 8

## Sheet 1 - Table 5-1-1
| Statistics, graphs and charts | [5 empty] | Total
| Planning and analysis | Adapt statistics | Implement sorting interface | Implement download interface | Implement graphs | User feedback and testing
Milko | 1 | 3 |  |  |  | 1 | 5
Alessandro | 1 |  | 1 | 1 | 5 | 2 | 10
Total days | 10

## Sheet 1 - Table 5-1-2
| Maps enhancements | [6 empty] | Total
| Planning and analysis | Develop measurement tool | Develop marker and tooltip manager | Develop layer system | Server side clustering | Heat maps | User feedback and testing
Milko | 2 |  |  |  | 9 |  | 3 | 14
Alessandro | 2 | 1 | 1 | 7 | 4 | 2 | 3 | 20
Total days | 20

## Sheet 1 - Table 2
Table 2
| Table data download | Login system | Dataset upload | Template data download | Portal management | Statistics, graphs and charts | Mapping component | Total
Milko | 6 | 16 | 30 | 12 | 4 | 5 | 14 | 87
Alessandro | 7 | 18 | 24 | 6 | 8 | 10 | 20 | 93